## Task Tracker
Task ID | Phase | Task | Description | Status | Due Date | Observation
T-01 | Phase 0 | Create project repository and folder structure | Create the kg-recsys GitHub repo, set up the folder structure (data/, notebooks/, src/, app/, docs/) and add a .gitignore | Not Started | May 6, 2026
T-02 | Phase 0 | Set up Python environment and install dependencies | Create a virtual environment and install core libraries: neo4j, streamlit, requests, pandas, pyvis, python-dotenv | Not Started | May 7, 2026
T-03 | Phase 0 | Download MovieLens 100K dataset | Download the ml-100k.zip from grouplens.org and place raw CSVs in data/raw/ | Not Started | May 7, 2026
T-04 | Phase 0 | Create Neo4j AuraDB free instance and save credentials | Spin up a free AuraDB instance at console.neo4j.io, download the credentials file, and store URI/user/password in .env | Not Started | May 8, 2026
T-05 | Phase 0 | Obtain TMDB API key | Create a free account at themoviedb.org, request a Developer API key (v3), and store it in .env as TMDB_API_KEY | Not Started | May 8, 2026
T-06 | Phase 1 | EDA on MovieLens raw files | Explore u.data (ratings), u.item (movies), and u.user (users) in notebooks/01_eda.ipynb. Document distributions, missing values, and key stats | Not Started | May 11, 2026
T-07 | Phase 1 | Enrich data via TMDB API | Build src/etl.py to call the TMDB API for each MovieLens movie and fetch cast, director, and genre data. Save enriched output to data/enriched/ | Not Started | May 15, 2026 | Mind the 40 req/10s rate limit
T-08 | Phase 1 | Design the Knowledge Graph schema | Define node labels (Movie, User, Actor, Director, Genre), relationship types, and key properties in notebooks/02_graph_schema.ipynb. Document design decisions | Not Started | May 18, 2026
T-09 | Phase 1 | Validate schema with a small sample load | Load 50 movies into Neo4j manually to verify schema correctness before the full ETL run | Not Started | May 18, 2026
T-10 | Phase 2 | Build entity loading scripts | Write scripts to MERGE Movie, User, Actor, Director, and Genre nodes into Neo4j using the neo4j Python driver | Not Started | May 21, 2026 | Use MERGE not CREATE to avoid duplicates
T-11 | Phase 2 | Build relationship loading scripts | Write scripts to create RATED, IN_GENRE, DIRECTED_BY, and FEATURES_ACTOR relationships with their properties | Not Started | May 22, 2026
T-12 | Phase 2 | Build derived relationship scripts | Compute and create COLLABORATED_WITH (actors who share a movie) and SIMILAR_TO (movies sharing actors/directors/genres) relationships | Not Started | May 23, 2026 | Run after all base relationships are loaded
T-13 | Phase 2 | Add Neo4j indexes and constraints | Create uniqueness constraints on node IDs and indexes on frequently queried properties (movie title, actor name) for query performance | Not Started | May 24, 2026
T-14 | Phase 2 | Full load validation | Verify node and relationship counts match expected totals. Run spot-check Cypher queries to confirm data integrity | Not Started | May 25, 2026
T-15 | Phase 3 | Write Cypher 101 notebook | Build notebooks/04_cypher_queries.ipynb with annotated examples: MATCH, WHERE, WITH, RETURN, and multi-hop traversals | Not Started | May 28, 2026
T-16 | Phase 3 | Document KG vs SQL comparison | Write side-by-side examples showing how multi-hop graph queries replace complex SQL JOINs. Include in the course docs | Not Started | May 29, 2026 | This is a key teaching moment for the course
T-17 | Phase 3 | Build graph.py helper module | Implement src/graph.py: Neo4j connection manager, parameterized query executor, and result formatter (list of dicts) | Not Started | May 30, 2026
T-18 | Phase 3 | Validate graph neighborhood in Neo4j Browser | Visually inspect the subgraph of 2-3 known movies and users in the Neo4j Browser to confirm relationships are correct | Not Started | May 30, 2026
T-19 | Phase 4 | Implement Strategy 1 — Genre affinity | Cypher: find genres the user rated >= 4.0, rank by frequency, recommend unseen movies in top genres | Not Started | Jun 1, 2026 | Simplest strategy — good baseline
T-20 | Phase 4 | Implement Strategy 2 — Director/Actor affinity | Cypher: extract directors and actors from highly-rated movies, find their other works the user hasn't seen (2-hop traversal) | Not Started | Jun 1, 2026
T-21 | Phase 4 | Implement Strategy 3 — Collaborative filtering via graph | Cypher: find users with overlapping high ratings, recommend what similar users liked that the target user hasn't seen | Not Started | Jun 4, 2026 | Most complex Cypher — plan the query carefully
T-22 | Phase 4 | Implement Strategy 4 — Composite multi-signal scoring | Combine signals from Strategies 1-3 with weights into a single ranked recommendation list | Not Started | Jun 6, 2026
T-23 | Phase 4 | Build recommender.py module | Wrap all 4 strategies in src/recommender.py with a unified interface: get_recommendations(user_id, strategy, limit) | Not Started | Jun 8, 2026
T-24 | Phase 5 | Build Screen 1 — User profile view | Streamlit page: user ID selector, rating history table, and pyvis subgraph of the user's immediate KG neighborhood | Not Started | Jun 10, 2026
T-25 | Phase 5 | Build Screen 2 — Recommendation engine | Streamlit page: strategy dropdown, recommendation results table, and explanation path for each recommendation | Not Started | Jun 11, 2026 | Explainability path is the key differentiator to highlight
T-26 | Phase 5 | Build Screen 3 — Graph explorer | Streamlit page: free-form entity search (movie or actor), renders the local subgraph using pyvis | Not Started | Jun 12, 2026 | 'Wow' screen for the demo
T-27 | Phase 5 | Polish Streamlit UX | Add loading spinners, empty-state messages, error handling, and sidebar navigation between screens | Not Started | Jun 13, 2026
T-28 | Phase 6 | Write setup guide | docs/01_setup.md: environment setup, Neo4j AuraDB provisioning, TMDB API key, and running the Streamlit app | Not Started | Jun 14, 2026
T-29 | Phase 6 | Write schema design module | docs/02_schema_design.md: explain each node/relationship choice and what queries each decision enables | Not Started | Jun 14, 2026
T-30 | Phase 6 | Write RecSys explained module | docs/03_recsys_explained.md: walkthrough of all 4 strategies with annotated Cypher, tradeoffs, and explainability examples | Not Started | Jun 15, 2026
T-31 | Phase 6 | Write overview doc — why KGs | docs/00_overview.md: limitations of tabular data for relational problems, KG value proposition, and project architecture overview | Not Started | Jun 15, 2026

## Legend
Status Legend
Not Started | Task has not been started yet
In Progress | Currently being worked on
Done | Completed successfully
Blocked | Blocked by a dependency or issue